## CO Summary
| OPM: |  |  |  | DISTRICT | [16 empty] | Construction Type: | new/add/reno/repair
| Designer: |  |  |  | School | [16 empty] | Reimbursement Rate: | %
| Contractor: |  |  |  | CHANGE ORDERS | [16 empty] | Approx. % Complete & SC Date
[22 empty] | Delivery Method: | DBB or CMR
| Description |  |  |  | Requested By | Net Added | Net Deducted | Rework Y / N? | Ineligible for Grant Participation | Additive PCO Eligible for Grant Participation | Deductive PCO Eligible for Grant Participation | Approximate Cost by Trade* | [6 empty] | Reason for Change** |  |  |  | Comment
PCO # | [11 empty] | Structural | Site | Utilities | Plumbing | Electrical | HVAC | Misc. | Design Issue | New Scope Directed by Owner | Differing Conditions | New Scope Directed by 3rd Party
| Change Order #001 | Execution Date: 12/24/21 | Submission Date: 3/1/22 | -20000
1 | Electrical for Elevator Pit Sump Pump |  |  |  | Designer | 5000 |  | N |  | 5000 | [5 empty] | 5000 |  |  | 5000 |  |  |  | Brief description of the scope of work and why it was necessary to be completed.
2 | Change from Terrazo Flooring to Linoleum Tile Throughout | [5 empty] | -25000 |  |  |  | -25000 | [6 empty] | -25000 |  | -25000
3
| Change Order #002 | Execution Date: 1/26/22 | Submission Date: 3/1/22 | 0
| Change Order #003 | Execution Date: 2/25/22 | Submission Date: 3/1/22 | 0
| Change Order #004 | Execution Date: 3/23/22 | Submission Date: 6/1/22 | 0
Change Order #008
Change Order #009
Change Order #010
Change Order #011
Change Order #012
Change Order #013
Change Order #014
Change Order #015
3 | Construction Contract Amount (without GMP Contingency) |  |  |  | 2000000 | 5000 | -25000 | 0 | 0 | 5000 | -25000 | 0 | 0 | 0 | 0 | 5000 | 0 | -25000 | 5000 | -25000 | 0 | 0
[6 empty] | 0.25% | -1.25% |  | 0% | 0.25% | -1.25% | 0% | 0% | 0% | 0% | 0.25% | 0% | -1.25% | 0.25% | -1.25% | 0% | 0%
[7 empty] | -20000 |  |  |  | -20000 | [6 empty] | -20000 |  |  |  | -20000
[7 empty] | -1% |  |  |  | -1% | [6 empty] | -1% |  |  |  | -1%
| Construction Change Order Summary | [10 empty] | SITE CAP |  |  |  |  | FF&E CAP |  |  |  |  | Change Orders Pending
| (Data Based on PFA, PFA Amendment No. 1) | [10 empty] | Base Project Cost |  |  | 35366614 |  | Furniture, Fixtures, and Equipment |  |  | 948000 |  | CO # | 0
1 | Construction Contract Amount (without GMP Contingency) | [5 empty] | 2000000 |  |  |  |  | Less Site work & Demo |  |  | -5131917 |  | Technology |  |  | 948000
2 | Total Construction Contingency Budget | [5 empty] | 100000 | [7 empty] | 30234697 |  | FF&E Subtotal |  |  | 1896000 |  | Total | 0
3 | Net Adjustments to Construction Contingency Budget by Approved Budget Revision Requests (BRR's). (Does not include budget transfers from Construction Contingency to Changes Orders) | [5 empty] | 0 | [7 empty] | 8%
4 | Construction Contract Amount (without GMP Contingency) (Including Total Construction Change Order Numbers 1-xx) (Line 1 + Line 13) | [5 empty] | 1980000 |  |  |  |  | SITE CAP MAXIMUM |  |  | 2418775.76 |  | Agreed Enrollment |  |  | 790
5 | Total Construction Change Orders as % of Construction Contract Amount (without GMP Contingency) (Line 13 / Line 1) | [5 empty] | -1% |  |  |  |  | PFA - Budget Site Costs |  |  | 4084288 |  | FFE $/student |  |  | 1200
6 | Total Construction Change Orders Eligible for Reimbursement as % of Total Construction Change Orders (Line 16 / Line 13) | [5 empty] | 100% |  |  |  |  | Budget Amt. Under/(Over) Cap |  |  | -1665512.24 |  | Technology $/student |  |  | 1200
7 | Total Construction Change Orders Eligible for Reimbursement as % of Construction Contract Amount (without GMP Contingency) (Line 16 / Line 1) | [5 empty] | -1% |  |  |  |  | Proposed Eligible Site Change Orders |  |  | 0
8 | Total Construction Change Orders Eligible for Reimbursement as % of Revised Total Construction Contingency Budget (Line 16 / Line 10) | [5 empty] | -20%
9 | Total Construction Change Orders Eligible for Reimbursement as % of Maximum Potentially Eligible Construction Contingency (Including Approved BRR's) (Line 16 / Line 12) | [5 empty] | -50%
PFA Budget
10 | Revised Total Construction Contingency Budget (Line 2 + Line 3) | [5 empty] | 100000
11 | Ineligible Construction Contingency Budget (If Any, Including Approved BRR's) | [5 empty] | 60000
12 | Maximum Potentially Eligible Construction Contingency (Including Approved BRR's) (Line 10 - Line 11) | [5 empty] | 40000
13 | Total Construction Change Order 1-xx | [5 empty] | -20000
14 | Total Additive Construction Change Orders Eligible for Reimbursement, Subject to Reimbursement Rate and Audit | [5 empty] | 5000
15 | Total Deductive Construction Change Orders Eligible for Grant Participation, Subject to Reimbursement Rate and Audit | [5 empty] | -25000
16 | Total Construction Change Orders Eligible for Reimbursement, Subject to Reimbursement Rate and Audit | [5 empty] | -20000
17 | Amount Remaining of Revised Total Construction Contingency Budget (Negative amount indicates insufficient Construction Contingency Budget. BRR required.) (Line 10 - Line 13) | [5 empty] | 120000
18 | Amount Remaining of Maximum Potentially Eligible Construction Contingency (Including Approved BRR's) (Negative amount indicates grant basis has been exceeded) (Line 12 - Line 14) | [5 empty] | 35000
19 | Total Credit Change Order Amount Reducing GMP Contingency | [5 empty] | 0
*The District must characterize the above specified categories including: a) Description, b) Requested by, c) Net Added/Deducted, d) Rework [stating yes or no], e) Amount Ineligible/Eligible for Grant Participation, f) Approximate Cost by Trade, g) Reason for the Change, and h) Comment [rationale/necessity] for the change).
Note on D8: Evan Levesque 6/28/22: Reflect the lastest date that the Change Order cover was signed.
Note on E8: Evan Levesque 6/28/22: Reflect the date that the MSBA PM received the executed Change Order backup documentation from the OPM.
Note on Q71: EL 6/29/21 - SD TPB, Substructure through Building Sitework.
Note on V71: EL 7/21/21 - SD TPB reimbursable Furniture, Fixtures and Equipment.
Note on Q72: EL 6/29/21 - SD TPB, Special Construction & Demolition through Building Sitework, reflected as a negative.
Note on V72: EL 7/21/21 - SD TPB reimbursable Technology.
Note on Q76: EL 6/29/21 - SD TPB, Building Sitework.
Note on V76: EL 7/21/21 - Should equal $1,200/student.
Note on V77: EL 7/21/21 - Should equal $1,200/student.

## Ineligible Comments
New scope by Owner is ineligible for grant participation.
New scope by thrid party is ineligible for grant participation.
Rework is ineligible for grant participation.
Site work over the site cap is ineligible for grant participation.
Costs beyond the scope of the PFA are ineligible for grant participation.
Costs associated with ineligible PCO's are also ineligible for grant participation.
Costs associated with [administration building, field house, concessions building, swimming pool, septic system, Alternate #X, etc.] are ineligible for grant participation.